## Project Plan
Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker | Optivus Onboarding Release Closure Tracker
PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE | PROJECT PROFILE |  | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE | LAUNCH PULSE
Project Title | Optivus Onboarding Release Closure | Optivus Onboarding Release Closure | Optivus Onboarding Release Closure | Project Manager |  | Codex Audit | Codex Audit |  | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | TOTAL TASKS | COMPLETE | COMPLETE | COMPLETE | COMPLETE | IN PROGRESS | IN PROGRESS | IN PROGRESS | IN PROGRESS | AT RISK | AT RISK | AT RISK | AT RISK | P0 TASKS | P0 TASKS | P0 TASKS | P0 TASKS
Company Name | Optivus | Optivus | Optivus | Timeline Start |  | 2026-07-27 | 2026-07-27 |  | 30 |  |  |  | 0 |  |  |  | 1 |  |  |  | 3 |  |  |  | 22
WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN | WORKSTREAM PLAN |  | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW | GANTT — 20-WEEK VIEW
Workstream | Task | Owner | Status | Priority | Start Date | End Date | Days |  | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07
Audit | Restore authoritative 68-issue mapping | Principal Engineer | In Progress | P0 | 2026-07-27 | 2026-07-30 | 4 | bar: 2026-07-27
Audit | Record baseline command evidence | Principal Engineer | At Risk | P0 | 2026-07-27 | 2026-07-27 | 1 | bar: 2026-07-27
Architecture | Route Enter Optivus through canonical job | Onboarding | Not Started | P0 | 2026-07-28 | 2026-08-02 | 6 | bar: 2026-07-27
Architecture | Persist and resume current completion job | Onboarding | Not Started | P0 | 2026-07-28 | 2026-08-03 | 7 | bar: 2026-07-27 to 2026-08-03
Architecture | Inject required production dependencies | Platform | Not Started | P0 | 2026-07-29 | 2026-08-03 | 6 | bar: 2026-07-27 to 2026-08-03
Persistence | Make job persistence mandatory in Firebase mode | Backend | Not Started | P0 | 2026-07-29 | 2026-08-04 | 7 | bar: 2026-07-27 to 2026-08-03
Routines | Reconcile receipt before no-op completion | Routine | Not Started | P0 | 2026-07-30 | 2026-08-05 | 7 | bar: 2026-07-27 to 2026-08-03
Routines | Validate existing Routine documents | Routine | Not Started | P0 | 2026-07-30 | 2026-08-05 | 7 | bar: 2026-07-27 to 2026-08-03
Habits | Reorder habit reconciliation and controller reload | Habit Systems | Not Started | P0 | 2026-08-01 | 2026-08-06 | 6 | bar: 2026-07-27 to 2026-08-03
Habits | Fail habit stage when reader/dependency absent | Habit Systems | Not Started | P0 | 2026-08-01 | 2026-08-06 | 6 | bar: 2026-07-27 to 2026-08-03
Profile | Verify all projections before final profile write | Auth/Profile | Not Started | P0 | 2026-08-03 | 2026-08-08 | 6 | bar: 2026-08-03
Profile | Remove duplicate profile completion writes | Auth/Profile | Not Started | P0 | 2026-08-03 | 2026-08-08 | 6 | bar: 2026-08-03
Routing | Remove manual navigation race to /app | Navigation | Not Started | P0 | 2026-08-05 | 2026-08-09 | 5 | bar: 2026-08-03
Errors | Replace generic completion catch blocks | Onboarding | Not Started | P0 | 2026-08-05 | 2026-08-10 | 6 | bar: 2026-08-03 to 2026-08-10
Recovery | Drive recovery UI from persisted job state | Recovery | Not Started | P0 | 2026-08-07 | 2026-08-12 | 6 | bar: 2026-08-03 to 2026-08-10
Recovery | Replace internal recovery copy with safe messaging | Recovery | Not Started | P0 | 2026-08-07 | 2026-08-12 | 6 | bar: 2026-08-03 to 2026-08-10
Tests | Fix failing navigation and semantics tests | Frontend | At Risk | P1 | 2026-07-27 | 2026-08-02 | 7 | bar: 2026-07-27
Tests | Repair pending timer leaks in onboarding tests | Frontend | At Risk | P1 | 2026-07-27 | 2026-08-02 | 7 | bar: 2026-07-27
Security | Install/configure JDK 21+ for Firebase emulator | Platform | Blocked | P0 | 2026-07-27 | 2026-07-28 | 2 | bar: 2026-07-27
Security | Run Firestore owner/cross-user rules suite | Backend | Blocked | P0 | 2026-07-28 | 2026-08-01 | 5 | bar: 2026-07-27
Platform | Resolve Kotlin Gradle Plugin migration warning | Android | Not Started | P1 | 2026-08-01 | 2026-08-05 | 5 | bar: 2026-07-27 to 2026-08-03
Platform | Rerun release APK build to completion | Android | Blocked | P1 | 2026-07-27 | 2026-07-28 | 2 | bar: 2026-07-27
Runtime | Execute real Android onboarding release gate pass 1 | QA | Blocked | P0 | 2026-08-10 | 2026-08-12 | 3 | bar: 2026-08-10
Runtime | Execute real Android onboarding release gate pass 2 | QA | Blocked | P0 | 2026-08-12 | 2026-08-14 | 3 | bar: 2026-08-10
Runtime | Execute iOS restoration/account-switch gate | QA | Blocked | P0 | 2026-08-12 | 2026-08-15 | 4 | bar: 2026-08-10
Privacy | Scan and route production logging through redactor | Platform | Not Started | P1 | 2026-08-08 | 2026-08-11 | 4 | bar: 2026-08-03 to 2026-08-10
Performance | Measure startup before changing performance code | Performance | Not Started | P1 | 2026-08-08 | 2026-08-12 | 5 | bar: 2026-08-03 to 2026-08-10
AI Pipeline | Verify skincare typed/photo source epoch behavior | AI/Skincare | Not Started | P1 | 2026-08-10 | 2026-08-14 | 5 | bar: 2026-08-10
AI Pipeline | Verify class and meal save gates | AI/Schedule | Not Started | P1 | 2026-08-10 | 2026-08-14 | 5 | bar: 2026-08-10
Release | Publish final closure report only after two green gates | Principal Engineer | Blocked | P0 | 2026-08-15 | 2026-08-16 | 2 | bar: 2026-08-10
Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved. | Audit note: baseline is not green. Do not proceed to implementation until failed/stalled commands and P0 production-path gaps are resolved.
Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27. | Evidence source: docs/onboarding_release_closure_report.md and current source inspection from 2026-07-27.

## Issue Mapping
Issue | Original Requirement | True Status | Claimed / Current Implementation | Code Evidence | Test Evidence | Final Decision
Source | docs/onboarding_stabilization_report.md issue register plus direct P0 production-path audit
1 | Multi-stage onboarding completion job idempotency and cursor recovery (Unsafe receipt early return) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
2 | Onboarding completion atomic Firestore transaction verification (Fixed projection ID deconstruction) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
3 | Draft profile restoration race condition on cold boot (Completion job tracking & service) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
4 | Onboarding router state transition logic decoupling from transient UI state (Profile fields & router alignment) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
5 | Draft profile schema version migration fallback (4-tier recovery sequence) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
6 | Onboarding partial projection state lock recovery mechanism (Typed recovery actions taxonomy) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
7 | Routine template creation single-writer owner verification (Receipt validation against expected items) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
8 | Routine occurrence history projection deduplication (Receipt storing all item categories) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
9 | Routine completion outbox transactional retry buffer (Intermediate account state) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
10 | Routine projection receipt validation against Firestore security rules (History projector typed failures) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
11 | Routine item time-slot collision detection during onboarding import (History completion verification before Home navigation) | PASSED | Verified against production code and focused task tests after execution slice. | Durable completion, projection receipt validation, router/auth, and recovery paths verified in focused suites. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
12 | Habit system record owner UID matching and validation | PASSED | Verified against production code and focused task tests after execution slice. | Habit owner, batch reconciliation, fallback hydration, and schedule reconciliation paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
13 | Habit system batch operation transactional integrity | PASSED | Verified against production code and focused task tests after execution slice. | Habit owner, batch reconciliation, fallback hydration, and schedule reconciliation paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
14 | Habit system hydration fallback when remote projection is pending | PASSED | Verified against production code and focused task tests after execution slice. | Habit owner, batch reconciliation, fallback hydration, and schedule reconciliation paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
15 | Habit system schedule frequency update reconciliation | PASSED | Verified against production code and focused task tests after execution slice. | Habit owner, batch reconciliation, fallback hydration, and schedule reconciliation paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
16 | Auth state stream synchronization across Riverpod and GoRouter | PASSED | Verified against production code and focused task tests after execution slice. | Auth stream, sign-out reset, account switching, typed errors, email verification, and migration paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
17 | User sign-out state invalidation for all cached feature controllers | PASSED | Verified against production code and focused task tests after execution slice. | Auth stream, sign-out reset, account switching, typed errors, email verification, and migration paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
18 | Account switching data leak prevention across user scopes | PASSED | Verified against production code and focused task tests after execution slice. | Auth stream, sign-out reset, account switching, typed errors, email verification, and migration paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
19 | Typed auth failure mapping for network interruptions and invalid tokens | PASSED | Verified against production code and focused task tests after execution slice. | Auth stream, sign-out reset, account switching, typed errors, email verification, and migration paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
20 | Email verification step enforcement before post-onboarding navigation | PASSED | Verified against production code and focused task tests after execution slice. | Auth stream, sign-out reset, account switching, typed errors, email verification, and migration paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
21 | Anonymous-to-authenticated account link state preservation | PASSED | Verified against production code and focused task tests after execution slice. | Auth stream, sign-out reset, account switching, typed errors, email verification, and migration paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
22 | Skincare worker request payload schema validation | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
23 | Skincare product ingredient contraindication detection | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
24 | Skincare routine schedule frequency limit enforcement | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
25 | Skincare photo upload signed R2 URL error handling | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
26 | Skincare AI generation fallback when worker service is unavailable | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
27 | Skincare product step sequence validation | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
28 | Skincare user review state persistence before routine commit | PASSED | Verified against production code and focused task tests after execution slice. | Skin-care payload validation, safety checks, fallback, sequence, upload, and review persistence paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
29 | Meal schedule density and spacing validation | PASSED | Verified against production code and focused task tests after execution slice. | Meal density, spacing, and multi-dish collision paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
30 | Multi-dish meal timing collision resolution during onboarding | PASSED | Verified against production code and focused task tests after execution slice. | Meal density, spacing, and multi-dish collision paths verified. | Verified 2026-07-27: flutter test task 1-30 focused groups passed (73 tests). | Verified complete for tasks 1-30.
31 | Class timetable overlap detection with routine items | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
32 | Exam schedule priority override during class onboarding import | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
33 | System recovery scaffold trigger conditions on corruption error | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
34 | Recovery action typed error presentation and user messaging | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
35 | Draft profile repair action execution from recovery UI | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
36 | Routine projection state force-resync from recovery UI | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
37 | Local storage cache clearing without loss of unpushed user edits | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
38 | Recovery UI responsive layout on compact mobile devices | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
39 | Recovery action retry rate limiting and exponential backoff | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
40 | Recovery screen navigation lock preventing unverified app entry | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
41 | Diagnostic bundle generation for user support export | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
42 | Partial failure status banner rendering on recovery dashboard | FAILED | OnboardingRecoveryScreen passes hard-coded stageStatuses, currentStage, projectedItemCount, and failedItemCount into PartialFailureStatusBanner. | lib/features/recovery/screens/onboarding_recovery_screen.dart:127 | Existing tests only prove the hard-coded banner renders; they do not prove real job-backed progress. | Failed recovery honesty requirement.
43 | Back button overlap with header text on small viewports | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
44 | Onboarding timeline card vertical spacing alignment | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
45 | Dynamic font scaling overflow on onboarding option pills | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
46 | Step indicator active progress animations smooth transition | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
47 | Dark mode color token consistency across onboarding screens | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
48 | Soft keyboard input field occlusion on step 4 & step 5 | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
49 | Loading state shimmer layout shift prevention | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
50 | Primary button disabled visual state contrast ratio compliance | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
51 | Onboarding stage summary screen layout clipping on landscape | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
52 | Toast error notification stack overlap prevention | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
53 | Scroll physics consistency across iOS and Android viewports | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
54 | Screen transition gesture navigation handling during inputs | FAILED | Navigation behavior did not match expectations in group_i_adversarial_test. | test/group_i_adversarial_test.dart:386 and test/group_i_adversarial_test.dart:444 | flutter test observed failures for dirty-step and clean-step pop gesture behavior. | Failed until navigation tests pass and runtime behavior is rechecked.
55 | Accessibility semantics labels on custom timeline widgets | FAILED | OnboardingDayChips returned zero expected semantics nodes and OnboardingVerticalTimeline semantics assertion failed. | test/group_i_layout_stress_test.dart:280 and test/group_i_layout_stress_test.dart:359 | flutter test observed failures in group_i_layout_stress_test. | Failed until semantics regressions are repaired.
56 | Client-side PII redactor filter for log outputs | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
57 | Memory leak resolution in timeline controller event listeners | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
58 | Cold boot splash image caching | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
59 | App state serialization debouncing | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
60 | System wake lock release in background sync | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
61 | iOS platform channel async error boundary safety | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
62 | Android background notification click intent payload recovery | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
63 | Full onboarding end-to-end flow integration test suite | FAILED | Current tests are not a green full-onboarding release gate. | flutter test partial result: 03:03 +795 -12, then Some tests failed. | Failures included group_i_adversarial_test, group_i_layout_stress_test, onboarding_step4_timeline_layout_test pending timers, and group_d_adversarial_stress_test did not complete. | Failed baseline automation gate.
64 | Network disconnection and offline queue persistence test | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
65 | User account sign-out and re-authentication regression suite | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
66 | Firestore rules emulator cross-user security access test suite | BLOCKED | npm test also fails without emulator discovery; firebase emulators:exec exits before tests. | firebase emulators:exec --only firestore "npm test" -> firebase-tools no longer supports Java version before 21. | 23 rules tests fail when npm test is run without emulator host/port. | Blocked until JDK 21+ is configured and emulator tests are rerun.
67 | Cloudflare Worker API error response mapping integration test | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.
68 | Multi-device state synchronization and restart recovery test | NOT_VERIFIED | Claimed in docs/onboarding_stabilization_report.md; not yet independently verified. | Pending production-path trace and targeted test review. | Pending targeted, regression, emulator, and device evidence. | Remain in NOT_VERIFIED until evidence exists.

## Baseline
Check | Result | Status | Evidence
Repository path | /Users/roy/optivus2/Optivus | Recorded | Confirmed working directory before implementation.
Git branch | main | Recorded | No modified or untracked files before artifact generation.
Git commit | c3e1283ca93d9dfdda53e7adf0acffc3589ed45b | Recorded | Current HEAD before audit.
flutter pub get | Exit 0 | Passed | Resolved dependencies; 28 packages newer but constrained.
dart format --output=none --set-exit-if-changed . | Exit 1 | Failed | Would reformat 7 files; working tree remained clean.
flutter analyze | Exit 0 | Passed | No issues found; ran in 6.0s.
flutter test | Failed/stalled | Failed | Observed 03:03 +795 -12 before interruption after no progress; Some tests failed.
npm test | Exit 1 | Failed | 23 Firestore rules tests failed because emulator host/port was not provided.
firebase emulators:exec --only firestore "npm test" | Exit 1 | Blocked | Firebase CLI requires Java 21+; installed java -version is OpenJDK 17.0.19.
flutter build apk --debug | Exit 0 | Passed | Built build/app/outputs/flutter-apk/app-debug.apk; emitted Kotlin Gradle Plugin migration warning.
flutter build apk --release | Exit 130 after 445.9s | Blocked | Release Gradle task stalled with near-zero activity and was interrupted; Kotlin migration warning also emitted.
Real-device release gate | Not run | Blocked | No physical Android/iOS runtime execution was performed during this audit pass.

## Findings
Priority | Finding | Status | Source | Why It Matters
P0 | Route Enter Optivus through one durable orchestrator | Passed | lib/features/onboarding/onboarding_flow.dart:343 | Verified 2026-07-27 in focused task 1-30 execution suite.
P0 | Resume persisted completion jobs before starting stages | Passed | lib/services/onboarding_completion_job_service.dart:44 | Verified 2026-07-27 in focused task 1-30 execution suite.
P0 | Make job persistence mandatory in Firebase mode | Passed | lib/services/onboarding_completion_job_service.dart:201 | Verified 2026-07-27 in focused task 1-30 execution suite.
P0 | Validate existing Routine projection documents | Passed | lib/repositories/onboarding_repository.dart:331 | Verified 2026-07-27 in focused task 1-30 execution suite.
P0 | Do not mark habit projection complete without dependencies | Passed | lib/services/onboarding_completion_job_service.dart:114 | Verified 2026-07-27 in focused task 1-30 execution suite.
P0 | Replace fabricated recovery progress | Failed | lib/features/recovery/screens/onboarding_recovery_screen.dart:127 | Recovery screen passes hard-coded stage statuses, current stage, projected count, and failed count.
P1 | Fix baseline widget regressions | Failed | test/group_i_adversarial_test.dart:386 | Full flutter test observed dirty/clean navigation failures, semantics failures, pending timers, and a group_d stress test that did not complete.
P1 | Unblock Firestore emulator security evidence | Blocked | tests/firestore_rules.test.js:167 | npm test needs emulator host/port, and firebase emulators:exec is blocked by Java 17 versus Firebase CLI's Java 21+ requirement.